## Automation
FlyCommerce Automation Tracker (Updated from current codebase)
No | Specs (Runner Files) | Scenarios (Describes/Scenarios) | Code | Test Cases (Functions) | Progress | Status | Comment | Extra | Comment | Progress | Status
Authentication - Login & Logout | [7 empty] | Extra | Comment | Progress | Status
1 | login.spec.ts | Login | L001 | userLogin | Completed | Passed |  | BeforeAll(): Navigate to login page |  | Completed | Passed
2 |  |  | L002 | userLogout | Completed | Passed |  | AfterAll(): Clear Cookies |  | Completed | Passed
Authentication - Registration | [7 empty] | Extra | Comment | Progress | Status
3 | registration.spec.ts | Registration | R001 | userRegistration | In-Progress | Flaky
4 |  |  | R002 | userRegistrationVerification1 | In-Progress | Failed | Stuck at Verification phase - due to Yopmail issues
5 |  |  | R003 | newUserLoginValidate | In-Progress | Flaky
6 |  |  | R004 | newUserLogoutValidate | In-Progress | Flaky
Marketplace Creation (FlyCommerce App - app.flycommerce.com) | [7 empty] | Extra | Comment | Progress | Status
7 | marketplaceOnboarding.spec.ts | FlyCommerce App Login | MC001 | flycommerceLogin | Completed | Passed |  | BeforeAll(): flycommercePage fixture |  | Completed | Passed
8 |  |  | MC002 | validateDokanCloudDashboard | Completed | Passed
9 |  | Create Marketplace | MC003 | fillMarketplaceOnboardingForm | Completed | Passed | name, build knowledge, team size, business status
10 |  |  | MC004 | fillAddressWithAutocomplete | Completed | Passed | ArrowDown+Enter autocomplete; fallback to manual Dhaka fill
11 |  |  | MC005 | verifyAddressFieldsPopulated | Completed | Passed | divisionDropdownTrigger + #state locator
12 |  |  | MC006 | submitMarketplaceCreation | Completed | Passed
13 |  | Preview Store | MC007 | verifyRedirectionToSetupGuide | Completed | Passed | Preview store host is validated from CUSTOMER_URL (supports prod/staging) | AfterAll(): Close optional chat widget |  | Completed | Passed
14 |  |  | MC008 | previewStoreSubdomain | Completed | Passed | Environment-aware host check from Urls.customerUrl
Marketplace Setup Guide (admin/setup-guide) | [7 empty] | Extra | Comment | Progress | Status
15 | setupGuide.spec.ts | Setup Guide Verification | SGP001 | verifySetupGuidePage | Completed | Passed | Verify setup guide loads | BeforeAll(): adminPage fixture |  | Completed | Passed
16 |  | General Settings | SGP002 | fillBusinessDetails | Completed | Passed | Fill phone & postal code | AfterAll(): Clear Cookies |  | Completed | Passed
17 |  | Brand Configuration | SGP003 | configureBrandSettings | Completed | Passed | Upload logo and favicon from URL | uploadImageFromURL() — reusable MediaManager method
18 |  | Payment Setup | SGP004 | configurePaymentSettings | Completed | Passed | Enable Test Gateway & Cash On Delivery
19 |  | Payout Setup | SGP005 | configurePayoutSettings | Completed | Passed | Configure bank transfer with flat + % fees
20 |  | Shipping Setup | SGP006 | configureShippingSettings | Completed | Passed | Enable shipping settings
21 |  | Full Setup Flow | SGP007 | completeSetupGuide | Completed | Passed | Complete all 5 steps end-to-end
Admin - Category Management | [7 empty] | Extra | Comment | Progress | Status
22 | categoryCreate.spec.ts | Create Category | ACC001 | createNewCategory | Completed | Passed |  | BeforeAll(): Admin Login |  | Completed | Passed
23 |  |  | ACC002 | validateCreatedCategory | Completed | Passed
24 | deleteCategory.spec.ts | Delete Category | ACC003 | deleteCategory | Completed | Passed |  | AfterAll(): Clear Cookies |  | Completed | Passed
25 |  |  | ACC004 | validateDeletedCategory | Completed | Passed
Admin - Brand Management | [7 empty] | Extra | Comment | Progress | Status
26 | brandCreate.spec.ts | Create Brand | ABR001 | createNewBrand | Completed | Passed |  | BeforeAll(): Admin Login |  | Completed | Passed
27 |  |  | ABR002 | validateCreatedBrand | Completed | Passed
28 | deleteBrand.spec.ts | Delete Brand | ABR003 | deleteBrand | Completed | Passed
29 |  |  | ABR004 | validateDeletedBrand | Completed | Passed
Admin - Product Collection Management | [7 empty] | Extra | Comment | Progress | Status
30 | collectionCreate.spec.ts | Create Collection | APC001 | createNewCollection | Completed | Passed |  | BeforeAll(): Admin Login |  | Completed | Passed
31 |  |  | APC002 | validateCreatedCollection | Completed | Passed
32 | deleteCollection.spec.ts | Delete Collection | APC003 | deleteCollection | Completed | Passed
33 |  |  | APC004 | validateDeletedCollection | Completed | Passed
Admin - Product Management | [7 empty] | Extra | Comment | Progress | Status
34 | deleteProduct.spec.ts | Delete Product | APM001 | deleteProduct | Completed | Passed |  | BeforeAll(): Admin Login |  | Completed | Passed
35 |  |  | APM002 | validateDeletedProduct | Completed | Passed
Admin - Vendor Management | [7 empty] | Extra | Comment | Progress | Status
36 | vendorCreate.spec.ts | Create Vendor | AVM001 | createVendor | Completed | Passed | Real geocodable address; state/city/zip fields added | BeforeAll(): Admin Login |  | Completed | Passed
37 |  |  | AVM002 | verifyVendorCreatedSuccessfully | Completed | Passed
Admin - Customer Management | [7 empty] | Extra | Comment | Progress | Status
38 | customerManagement.spec.ts | Customer Management | ACM001 | viewCustomerList | Completed | Passed |  | BeforeAll(): Admin Login |  | Completed | Passed
39 |  |  | ACM002 | validateCustomerData | Completed | Passed
Vendor - Login & Product Creation | [7 empty] | Extra | Comment | Progress | Status
40 | vendorLogin.spec.ts | Vendor Login | VL001 | vendorLogin | Completed | Passed |  | BeforeAll(): vendorPage fixture |  | Completed | Passed
41 | productCreate.spec.ts | Create Product | VPC001 | createNewProduct | Completed | Passed | With images and full product details
42 |  |  | VPC002 | validateCreatedProduct | Completed | Passed
43 |  |  | VPC003 | publishProduct | Completed | Passed
44 | e2eDeleteProductRelatedThings.spec.ts | E2E Delete Flow | VPC004 | deleteProductRelatedThingsE2E | Completed | Passed | Serial deletion: product + related items
Customer - Authentication (Implemented) | [7 empty] | Extra | Comment | Progress | Status
45 | customerLogin.spec.ts | Login with Email | CL001 | loginWithEmail | Completed | Passed |  | customerAuthPage.ts implemented
46 |  |  | CL002 | validateSuccessfulLogin | Completed | Passed
47 |  | Forgot Password | CL003 | forgotPassword | Planned | Not Implemented | Forgot password scenario not in current spec scope
48 |  |  | CL004 | validatePasswordResetEmail | Planned | Not Implemented | Password reset email validation not in current spec scope
49 | customerRegistration.spec.ts | Registration with Email | CR001 | registrationWithEmail | Planned | Not Implemented | customerRegistration.spec.ts does not exist in codebase
50 |  |  | CR002 | validateRegistrationSuccess | Planned | Not Implemented
51 | customerLogout.spec.ts | Logout | CLO001 | customerLogout | Planned | Not Implemented | customerLogout.spec.ts does not exist in codebase
52 |  |  | CLO002 | validateLogout | Planned | Not Implemented
53 | customerSecurity.spec.ts | Access Control | CS001 | accessMyAccountWithoutLogin | Planned | Not Implemented | customerSecurity.spec.ts does not exist in codebase
54 |  |  | CS002 | validateRedirectToLogin | Planned | Not Implemented
Customer - Cart & Checkout (Implemented) | [7 empty] | Extra | Comment | Progress | Status
55 | addToCart.spec.ts | Add to Cart | CCT001 | addProductToCart | Completed | Passed | Single add-to-cart smoke test implemented (seed product) | cartPage.ts implemented
56 |  |  | CCT002 | validateCartItem | Covered | Passed | Validated inside checkout journey/cart assertions
57 |  | Apply Coupon | CCT003 | applyCouponCodeValidate | Planned | Not Implemented | Coupon scenario not in current scope
58 |  |  | CCT004 | validateCouponDiscount | Planned | Not Implemented | Coupon discount scenario not in current scope
59 | checkout.spec.ts | Checkout Flow | CCO001 | contactInformationValidate | Completed | Passed | checkout.spec.ts covers end-to-end COD checkout | checkoutPage.ts implemented
60 |  |  | CCO002 | shippingAddressValidate | Covered | Passed | Shipping address validated in checkout flow
61 |  |  | CCO003 | paymentMethodValidate | Covered | Passed | Payment method (COD) validated in checkout flow
62 |  |  | CCO004 | placeOrderValidate | Covered | Passed | Place order validated in checkout flow
63 |  |  | CCO005 | validateOrderConfirmation | Covered | Passed | Order confirmation validated in checkout flow
Admin - Subscription Plans (Phase 3 — Pending) | [7 empty] | Extra | Comment | Progress | Status
64 | subscriptionPlan.spec.ts | Create Subscription Plan | ASP001 | createSubscriptionPlan | Pending | - | subscriptionPlanPage.ts not created yet
65 |  |  | ASP002 | validateCreatedPlan | Pending | -
66 | vendorOnboarding.spec.ts | Vendor Purchase Plan | VOB001 | vendorPurchasePlan | Pending | - | vendorOnboardingPage.ts not created yet
67 |  |  | VOB002 | validatePlanActivated | Pending | -
68 | e2eCommissionVerification.spec.ts | Commission on Sale | VOB003 | verifyCommissionApplied | Pending | -
Standalone Store Onboarding (Phase 4 — Pending) | [7 empty] | Extra | Comment | Progress | Status
69 | standaloneOnboarding.spec.ts | Create Standalone Store | SSO001 | createStandaloneStore | Pending | - | standaloneOnboardingPage.ts not created yet
70 |  |  | SSO002 | validateStoreCreated | Pending | -
E2E - Full Business Flow (Phase 5 — Pending) | [7 empty] | Extra | Comment | Progress | Status
71 | e2eFullBusinessFlow.spec.ts | Marketplace → Setup → Product → Purchase | E2E001 | createMarketplaceE2E | Pending | -
72 |  |  | E2E002 | setupMarketplaceE2E | Pending | -
73 |  |  | E2E003 | vendorCreateProductE2E | Pending | -
74 |  |  | E2E004 | customerPurchaseProductE2E | Pending | -
75 | e2eCommissionFlow.spec.ts | Commission Verification E2E | E2E005 | verifyCommissionE2E | Pending | -